## Sheet1
Budget, Scope, & Time estimates
Scope & Time Estimate
Task | Time Estimate (in hours) | Start Date | End Date
1. Project Management (PM) | 500 | 2025-02-05 | 2025-04-21
- 1.1 Project Initiation and Planning | 200 | 2025-02-05 | 2025-03-05
- 1.2 Risk Management | 100 | 2025-03-10 | 2025-03-31
- 1.3 Stakeholder Communication and Coordination | 100 | 2025-04-01 | 2025-04-07
- 1.4 Project Tracking and Reporting | 100 | 2025-04-08 | 2025-04-21
2. Requirements Analysis and Planning | 600 | 2025-04-22 | 2025-05-16
- 2.1 Gather Requirements from Stakeholders | 175 | 2025-04-22 | 2025-04-28
- 2.2 Define System Functionalities and Features | 225 | 2025-04-29 | 2025-05-10
- 2.3 Document Data Storage and Retrieval Needs | 200 | 2025-05-12 | 2025-05-16
3. System Design and Architecture | 850 | 2025-05-17 | 2025-07-28
- 3.1 Database Design and Development | 300 | 2025-05-17 | 2025-06-13
- 3.2 User Interface Design | 250 | 2025-06-16 | 2025-07-06
- 3.3 Reporting Functionality Design | 150 | 2025-07-06 | 2025-07-21
- 3.4 Security and Compliance Planning | 150 | 2025-07-22 | 2025-07-28
4. System Development | 1300 | 2025-07-28 | 2025-11-28
- 4.1 Front-end Development | 500 | 2025-07-28 | 2025-08-29
- 4.2 Back-end Development | 500 | 2025-08-30 | 2025-09-30
- 4.3 Database Implementation | 300 | 2025-10-01 | 2025-11-28
5. Deployment and Training | 430 | 2025-11-29 | 2026-03-06
- 5.1 Deployment Planning and Execution | 180 | 2025-12-12 | 2026-02-12
- 5.2 End-user Training | 250 | 2026-02-13 | 2026-03-06
6. Documentation and Transfer | 300 | 2026-03-06 | 2026-05-05
- 6.1 System Documentation | 150 | 2026-03-06 | 2026-04-06
- 6.2 Knowledge Transfer | 150 | 2026-04-07 | 2026-05-05
7. Post-Implementation | 170 | 2026-05-06 | 2026-07-06
- 7.1 Performance Monitoring and Optimization | 70 | 2026-05-05 | 2026-06-08
- 7.2 Issue Resolution and Support | 100 | 2026-06-09 | 2026-07-06
Budget Estimate
Task | Labor (in hours) | Cost per Hour ($) | Total Labor Cost ($) | Non-Labor Cost ($) | Total Cost ($) | 15% Reserve ($) | Final Total Cost ($)
1. Project Management (PM) | 500 | 50 | 25000 | 10000 | 35000 | 5250 | 40250
- 1.1 Project Initiation and Planning | 200 | 50 | 10000 | 2500 | 12500 | 1875 | 14375
- 1.2 Risk Management | 100 | 50 | 5000 | 1500 | 6500 | 975 | 7475
- 1.3 Stakeholder Communication and Coordination | 100 | 50 | 5000 | 2500 | 7500 | 1125 | 8625
- 1.4 Project Tracking and Reporting | 100 | 50 | 5000 | 3500 | 8500 | 1275 | 9775
2. Requirements Analysis and Planning | 600 | 40 | 24000 | 12500 | 36500 | 5475 | 41975
- 2.1 Gather Requirements from Stakeholders | 175 | 40 | 7000 | 2000 | 9000 | 1350 | 10350
- 2.2 Define System Functionalities and Features | 225 | 40 | 9000 | 4000 | 13000 | 1950 | 14950
- 2.3 Document Data Storage and Retrieval Needs | 200 | 40 | 8000 | 6500 | 14500 | 2175 | 16675
3. System Design and Architecture | 850 | 55 | 46750 | 17500 | 64250 | 9637.5 | 73887.5
- 3.1 Database Design and Development | 300 | 55 | 16500 | 5000 | 21500 | 3225 | 24725
- 3.2 User Interface Design | 250 | 55 | 13750 | 6000 | 19750 | 2962.5 | 22712.5
- 3.3 Reporting Functionality Design | 150 | 55 | 8250 | 4000 | 12250 | 1837.5 | 14087.5
- 3.4 Security and Compliance Planning | 150 | 55 | 8250 | 2500 | 10750 | 1612.5 | 12362.5
4. System Development | 1300 | 60 | 78000 | 40000 | 118000 | 17700 | 135700
- 4.1 Front-end Development | 500 | 60 | 30000 | 10000 | 40000 | 6000 | 46000
- 4.2 Back-end Development | 500 | 60 | 30000 | 15000 | 45000 | 6750 | 51750
- 4.3 Database Implementation | 300 | 60 | 18000 | 15000 | 33000 | 4950 | 37950
5. Deployment and Training | 430 | 45 | 19350 | 12000 | 31350 | 4702.5 | 36052.5
- 5.1 Deployment Planning and Execution | 180 | 45 | 8100 | 4000 | 12100 | 1815 | 13915
- 5.2 End-user Training | 250 | 45 | 11250 | 8000 | 19250 | 2887.5 | 22137.5
6. Documentation and Transfer | 300 | 35 | 10500 | 8000 | 18500 | 2775 | 21275
- 6.1 System Documentation | 150 | 35 | 5250 | 5000 | 10250 | 1537.5 | 11787.5
- 6.2 Knowledge Transfer | 150 | 35 | 5250 | 3000 | 8250 | 1237.5 | 9487.5
7. Post-Implementation | 170 | 30 | 5100 | 5000 | 10100 | 1515 | 11615
- 7.1 Performance Monitoring and Optimization | 70 | 30 | 2100 | 3000 | 5100 | 765 | 5865
- 7.2 Issue Resolution and Support | 100 | 30 | 3000 | 2000 | 5000 | 750 | 5750
Total | 4150 |  | 417400 | 210000 | 627400 | 94110 | 721510