## Sheet1
A.I.M. Project - Risk Register
|  | No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Response | Risk Owner | Probability | Impact | Status | Risk Response Strategy
| Initiating | Int1.1 | 6 | E prjt team | Early formation of project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Some of the team members are new to Awesome University and there availability schedules are still unknown. | Excelsior! Start creating the project contract. | PM Unit | high | low | N/A | Acceptance
|  | Int1.2 | 3 | D prjt team | Delayed formation of project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Some of the team members are new to Awesome University and there availability schedules are still unknown. | Give the team members a deadline to respond if they will or will not participate with a mid-term reminder if needed. | PM Unit | low | medium | N/A | Mitigation
|  | Int1.3 | 1 | F prjt team | Failure to form project team | FF4 | A team needed to be created for this project and we generally know all of the members but we do not know their availiability | Some of the team members are new to Awesome University and there availability schedules are still unknown. | Search for other team members at Awesome University or consider outsourcing. | PM Unit | low | high | N/A | Mitigation
|  | Int2.1 | 6 | E prjt contract | Early completion of project contract | FF4 | A contract is needed to ensure all on of the project members are onboard and agree with their role in the project. We are uncertain if all members agree with their roles. | Some of the team members are new to Awesome University and may or may not agree on their role in the project. | Outstanding! Start creating the project plan. | PM Unit | high | low | N/A | Acceptance
|  | Int2.2 | 3 | D prjt contract | Delay in completion of project contract | FF4 | A contract is needed to ensure all on of the project members are onboard and agree with their role in the project. We are uncertain if all members agree with their roles. | Some of the team members are new to Awesome University and may or may not agree on their role in the project. | Speak with the team members to understand their issues and see if a compromise can be reached. | PM Unit | low | medium | N/A | Mitigation
|  | Int2.3 | 1 | F prjt contract | Failure to complete project contract | FF4 | A contract is needed to ensure all on of the project members are onboard and agree with their role in the project. We are uncertain if all members agree with their roles. | Some of the team members are new to Awesome University and may or may not agree on their role in the project. | Speak with the team members to understand their issues and see if a compromise can be reached. If not, a new team member will need to be recruited. | PM Unit | low | high | N/A | Mitigation
| Planning | Plan1.1 | 6 | E prjt plan | Early completion of project plan | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | We are uncertain of each team member's time management skills. | Fabulous! Contact the committee to put our project plan on the agenda. | PM Unit | high | low | N/A | Acceptance
|  | Plan1.2 | 3 | D prjt plan | Delay in completion of project plan | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | We are uncertain of each team member's time management skills. | Set a deadline for the team members and send reminders and ask for progress reports. | PM Unit | low | medium | N/A | Mitigation
|  | Plan1.3 | 1 | F prjt plan | Failure to complete project plan | FF4 | A project plan is to be submitted to the committee and its parts are being constructed by different team members. We are uncertain of each member's time management skills. | We are uncertain of each team member's time management skills. | If the deadline for submission to the committee is missed, reassess the team member's position and potentially replace. Resubmit to the committee next year. | PM Unit | low | high | N/A | Mitigation
|  | Plan2.1 | 2 | D committee | Delay in committee project plan approval | T | The plan for the online courses needs to be approved by the committee before the project can proceed. The committee's meeting schedule might change due to undetermined circumstances (such as COVID-19, hurricane evacuations). | Unforseen events such as a pandemic or hurricane evacuation can delay the committee from meeting. | Adjust the dates in the project charter and resubmit to the committee if needed. | PM Unit | low | medium | N/A | Acceptance
|  | Plan2.2 | 1 | Epic FAIL! | Denial of project plan approval by committee | Xmen | The plan for the online courses needs to be approved by the committee before the project can proceed. | The committee may feel the project charter is incomplete, inaccurate, etc. | Understand the committee's feedback and resubmit the next year. | PM Unit | low | high | N/A | Acceptance
|  | Plan3 | 2 | Increse Salaries | Increase in salaries as issued by the state government | Xmen | The plan's budget does not take into account wage increases by the government. | Annual raises do take place but sometime the rate is innacurately calculated and can throw off the budget approved by the university's approval committee. | Contacting the committee for an increase of project budget. | PM Unit | medium | medium | N/A | Transference
|  | Plan4.1 | 6 | E Hardware & Software | Early delivery of hardware and software | Xmen | Special software features for video production needs delivery. We are uncertain of its availabiity. | Software arrives early due to an efficent university mail system. | Great! Start constructing the WBS. | PM Unit | low | low | N/A | Acceptance
|  | Plan4.2 | 3 | D Hardware & Software | Delay in delivery of hardware and software | Xmen | Special software features for video production needs delivery. We are uncertain of its availabiity. | Software is out of stock temporairly or is delayed by the university mail system | Continue on with creating the WBS as it is not dependant on the software for video and graphic enhancements. | PM Unit | medium | medium | N/A | Acceptance
|  | Plan4.3 | 3 | I Hardware &Software | Increase in price of hardware and software | Xmen | Special software features for video production needs delivery. We are uncertain if it will change from the cost as noted in the project charter. | Software costs quoted in the project charter costs differently. | Adjust the budget if possible dependent on the price increase, find other equivalently priced software or work without it. | PM Unit | medium | medium | N/A | Acceptance
|  | Plan4.4 | 5 | De Hardware & Software | Decrease in the price of hardware and software | Xmen | Special software features for video production needs delivery. We are uncertain if it will change from the cost as noted in the project charter. | Software costs quoted in the project charter costs differently. | Note the decrease and funnel it back into resources. | PM Unit | low | low | N/A | Acceptance
|  | Plan4.5 | 2 | F Hardware & Software | Failure in delivery of software and hardware | Xmen | Special software features for video production needs delivery. We are uncertain of its availabiity. | Software is not available for purchase at the university. | Potential outsourcing for software is needed. | PM Unit | low | medium | N/A | Transference
|  | Plan5.1 | 6 | E WBS | Early completion of WBS | FF4 | A WBS is essential to workflow of the project. However, there are pieces of the work flow that are new or tasks are getting reordered. | Team members work well, efficently and are able to adapt the WBS easily finishing early. | Adjust the WBS and add the extra time to course design and development. | PM Unit | high | low | N/A | Acceptance
|  | Plan5.2 | 3 | D WBS | Delay in Completion of WBS | FF4 | A WBS is essential to workflow of the project. However, there are pieces of the work flow that are new or tasks are getting reordered. | Team members miss initial deadline for WBS completion | Project manager sets second deadline, speaks with team members to assess the delay and asks for daily progress reports on the WBS. WBS creation is origianally 5 days and now will extend to 8. Time is adjusted on the WBS by taking time away from design and development. | PM Unit | low | medium | N/A | Mitigation
|  | Plan5.3 | 2 | F WBS | Failure to complete WBS | FF4 | A WBS is essential to workflow of the project. However, there are pieces of the work flow that are new or tasks are getting reordered. | Team members miss more than 2 deadlines for WBS completion | Second deadline is missed. Project manager completes the WBS, takes the missed time away from design and development and assess the problem by speaking with team members. | PM Unit | low | high | N/A | Mitigation
Course Production - Phases 1 & 2 | Analysis, Pre-production & Planning | Ana1.1 | 3 | D course des packet | Delay in course design package request | FF4 | The course is not complete until we meet with the SME and have the course materials being delivered by course directors. Only after this meeting can we better assess the design package request. | SME schedules are not either lining up with the ID unit or have not responded to ID unit's emails or phone calls on scheduling. -or- Course director materials have not arrived. | Second attempt to contact the SME for a meeting and/or contact course directors for materials. Any missed time will be time taken away from design and development. | PM Unit | low | medium | N/A | Mitigation
|  | Ana1.2 | 2 | F course des packet | Failure to complete design package request | FF4 | The course is not complete until we meet with the SME and have the course materials being delivered by course directors. Only after this meeting can we better assess the design package request. | SME schedules are not either lining up with the ID unit or have not responded to ID unit's emails or phone calls on scheduling after 5 tries. -or- Course materials do not arrive. | Find other SME and/or personally pick-up the course director materials. Any missed time will be time taken away from design and development. | PM Unit | low | high | N/A | Transference
|  | Ana2.1 | 5 | E course map | Early completion of course map | FF4 | The course map is incomplete until our meeting with the SME. We are unaware of the SME's schedules or when the course materials from course directors will be delivered. | Meeting with the SME and delivery of the course materials is early. | Adjust time, and add it to design and development of courses. | PM Unit | high | low | N/A | Acceptance
|  | Ana2.2 | 3 | D course map | Delay in completed of course map | FF4 | The course map is incomplete until our meeting with the SME. We are unaware of the SME's schedules or when the course materials from course directors will be delivered. | Meeting with the SME and delivery of the course materials misses deadline. | Set the second deadline for in 3 days and ask for daily progress reports from team members. Adjust time but taking it away from design and development. | PM Unit | low | medium | N/A | Mitigation
|  | Ana2.3 | 2 | F course map | Failure to complete course map | FF4 | The course map is incomplete until our meeting with the SME. We are unaware of the SME's schedules or when the course materials from course directors will be delivered. | Meeting with the SME and delivery of the course materials misses second deadline. | Pick up the course materials from course directors and find other SME. Any missed time will be taken away from design and development. | PM Unit | low | medium | N/A | Transference
|  | Des1.1 | 6 | E SME | Early consultation with SME |  | We currently do not know the SME's schedules or when the course materials from course directors will be delivered. This meeting is essential for the course map and design package. | Able to schedule meetings with SME and early delivery of course director materials. | Outstanding! Start creating the graphic design concept. | ID Unit | high | low | N/A | Acceptance
| Design | Des1.2 | 3 | D SME | Delay in consultations with SME | FF4 | We currently do not know the SME's schedules or when the course materials from course directors will be delivered. This meeting is essential for the course map and design package. | Missed first deadline with SME and/or course director materials were not delivered. | Make a second deadline for 2 days out and ask for daily progress reports | ID Unit | low | medium | N/A | Mitigation
|  | Des1.3 | 2 | F SME | Failure to meet with SME | FF4 | We currently do not know the SME's schedules or when the course materials from course directors will be delivered. This meeting is essential for the course map and design package. | Missed second deadline with SME and / or course director materials were not delivered. | Pick up the course materials from course directors and find other SME. Any missed time will be taken away from development. | ID Unit | low | high | N/A | Transference
|  | Des2.1 | 5 | E graphic concept | Early completion of graphic design concept | FF4 | The graphic design concept is contingent on the visual content which are completed by separate team members on different schedules. | Good communication and collaboration between ID unit and MM unit. | Combine reports and submit content graphic request. Additional time will be added to development. | ID Unit | high | low | N/A | Acceptance
|  | Des2.2 | 3 | D graphic concept | Delay in completion of graphic design concept | FF4 | The graphic design concept is contingent on the visual content which are completed by separate team members on different schedules. | First deadline is not met by either the ID unit or the MM unit, or both. | Set a second deadline for 2 days and ask for progress reports from each unit. | ID Unit | low | medium | N/A | Mitigation
|  | Des2.3 | 2 | F graphic concept | Failure to complete graphic design concept | FF4 | The graphic design concept is contingent on the visual content which are completed by separate team members on different schedules. | Second deadline is not met by either unit or both. | Set a third deadline for 1 day. Missed time will be taken away from development. | ID Unit | low | high | N/A | Mitigation
|  | Des3.1 | 5 | E visual content | Early completion of visual content | FF4 | The visual content is contingent on the graphic design concept which are completed by separate team members on different schedules. | Good communication and collaboration between ID unit and MM unit. | Combine reports and submit content graphic request. Additional time will be added to development. | MM Unit | high | low | N/A | Acceptance
|  | Des3.2 | 3 | D visual content | Delay competing of visual content | FF4 | The visual content is contingent on the graphic design concept which are completed by separate team members on different schedules. | First deadline is not met by either the ID unit or the MM unit, or both. | Set a second deadline for 2 days and ask for progress reports from each unit. | MM Unit | low | medium | N/A | Mitigation
|  | Des3.3 | 2 | F visual content | Failure to complete visual content | FF4 | The visual content is contingent on the graphic design concept which are completed by separate team members on different schedules. | Second deadline is not met by either unit or both. | Set a third deadline for 1 day. Missed time will be taken away from development. | MM Unit | low | high | N/A | Mitigation
|  | Des4.1 | 6 | E graphic request | Early submission for content graphics requests | FF4 | The visual content and the graphic content need to be submitted together and each portion is completed by a separate team member on different schedules. | Good communication and collaboration between ID unit and MM unit. Result, the content graphics request is sent in early. | Excelsior! ID unit can start creating the canvas courses and MM unit the videos. | ID Unit | high | low | N/A | Acceptance
|  | Des4.2 | 3 | D graphic request | Delay in submission for content graphics requests | FF4 | The visual content and the graphic content need to be submitted together and each portion is completed by a separate team member on different schedules. | First deadline is not met by either the ID unit or the MM unit, or both. | Set a second deadline for 2 days and ask for progress reports from each unit. | ID Unit | low | medium | N/A | Mitigation
|  | Des4.3 | 2 | F graphic request | Failure to submit content graphics requests | FF4 | The visual content and the graphic content need to be submitted together and each portion is completed by a separate team member on different schedules. | Second deadline is not met by either unit or both. | Set a third deadline for 1 day. Missed time will be taken away from development. | ID Unit | low | high | N/A | Mitigation
|  | Des5.1 | 5 | E assessments | Early completion of designing practical tasks, quizzes, tests | FF4 | These are being designed by the team members who are also in the ID unit and MM unit who are on different schedules. | Good communication and collaboration between ID unit and MM unit resulting in early completion of practical tasks, quizzes and tests for courses. | Outstanding! Upload information to Canvas course shells once created. Extra time will be added to development | Eval Unit | high | low | N/A | Acceptance
|  | Des5.2 | 3 | D assessments | Delay in completion of designing practical tasks, quizzes, tests | FF4 | These are being designed by the team members who are also in the ID unit and MM unit who are on different schedules. | First deadline is not met by either the ID unit or the MM unit, or both. | Set a second deadline for 2 days and ask for progress reports from each unit. | Eval Unit | low | medium | N/A | Mitigation
|  | Des5.3 | 2 | F assessments | Failure to complete designing practical tasks, quizzes, tests | FF4 | These are being designed by the team members who are also in the ID unit and MM unit who are on different schedules. | Second deadline is not met by either unit or both. | Set a third deadline for 1 day. Missed time will be taken away from development. | Eval Unit | low | high | N/A | Mitigation
| Development | Dvp1.1 | 3 | Software glitch | Software malfunction with Canvas | Tech | Canvas is our electronic platform for our LMS. It is essential IT has this available for course construction. | Delays can include weaterh issues such as power outages due to lightning or longer lasting such as a hurricane evacuation when Canvas may not be available. | Determine the duration delay and adjust the schedule if needed. | PM Unit | low | medium | N/A | Acceptance
|  | Dvp1.2 | 1 | F Software | Software failure with Canvas | Tech | Canvas is our electronic platform for our LMS. It is essential IT has this available for course construction. | Delays can include weaterh issues such as power outages due to lightning or longer lasting such as a hurricane evacuation when Canvas may not be available for some time as opposed to over night. | Determine the delay duration and adjust the schedule if needed. Contact IT and assess the duration if it will be more than 2 days, adjust time accordingly. | PM Unit | low | medium | N/A | Acceptance
|  | Dvp2.1 | 3 | D course shell | Delay in course shell creation from IT | Xmen | IT is creating the course shell for the Canvas courses in which the ID will construct the course. Delay in IT creating a course shell will delay course creation in Canvas. | Course is not created within the 24 hour window as noted by IT. | Contact IT and assess the duration's delay. Adjust schedule if needed. | PM Unit | low | medium | N/A | Acceptance
|  | Dvp2.2 | 1 | F course shell | Failure in course shell creation from IT | Xmen | IT is creating the course shell for the Canvas courses in which the ID will construct the course. Faliure for IT to create course shells will stop course creation in Canvas. Failure can occur in Risk Dvp. 1.2 | Course is not created within the 48 hour window as noted by IT. | Contact IT and assess the duration's delay. Adjust schedule if needed. If it will be more than 2 days, adjust time accordingly. | PM Unit | low | high | N/A | Acceptance
|  | Dvp3.1 | 6 | E course materials | Early delivery of course materials from course directors needed for creating Canvas courses | FF4 | Course materials are essential for course creation. We are uncertain when they are to be delivered from course directors. However, a deadline has been created for them. | Course directors deliver their materials before the deadline. | Outstanding! Continue with creating Canvas courses. Additional time added to ID unit and MM unit development time. | ID Unit | medium | low | N/A | Acceptance
|  | Dvp3.2 | 3 | D course materials | Delay in delivery of course materials from course directors needed for creating Canvas courses | FF4 | Course materials are essential for course creation. We are uncertain when they are to be delivered from course directors. However, a deadline has been created for them. | Course directors deliver their materials after the deadline. | Set a second deadline for 2 days and communicate this to course directors. | ID Unit | medium | medium | N/A | Mitigation
|  | Dvp3.3 | 2 | F course materials | Failure in deliver of course materials from course directors needed for creating Canvas courses | FF4 | Course materials are essential for course creation. We are uncertain when they are to be delivered from course directors. However, a deadline has been created for them. | Course directors deliver their materials after the second deadline. | Pick up the course director materials personally. Time will be reduced in ID unit and MM unit development time. | ID Unit | low | high | N/A | Mitigation
|  | Dvp4.1 | 5 | E ID | Early completion of instructional design | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | ID unit has all the needed materials and is able to finish ahead of schedule. | Check to see assistance is needed with eval or MM units. | ID Unit | medium | low | N/A | Acceptance
|  | Dvp4.2 | 3 | D ID -tech | Delay in completion of instructional design due to technical difficulties | Tech | We do not have the course shells created by IT. After they are created only then can course creation begin. | ID unit does not have the Canvas course shells created by IT to develop the courses. | Contact IT to understand the delay and it's duration. | ID Unit | low | low | N/A | Acceptance
|  | Dvp4.3 | 3 | D ID - HR | Delay in completion of instructional design due to human error and issues | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | ID unit missed the first deadline due to not receiving the materials from course directors and/or meeting with SME on time. | Contact course directors for materials and SME for meetings. A second deadline is set ASAP. | ID Unit | low | medium | N/A | Mitigation
|  | Dvp4.4 | 2 | F ID | Failure to complete instructional design | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | ID unit missed the second deadline due to not receiving the materials from course directors and/or meeting with SME on time. | Pick-up course director materials after the second deadline. If SME have not responded find a new one in 24-hrs. | ID Unit | low | high | N/A | Mitigation
|  | Dvp5.1 | 5 | E vid | Early completion of videos | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | MM unit has all needed materials and is able to finish ahead of schedule. | Stupendous! Add materials to ID unit's courses. | MM Unit | medium | low | N/A | Acceptance
|  | Dvp5.2 | 3 | D vid - tech | Delay in completion of videos due to technical difficulties | Tech | Due to unforseen issues with electrical equipment, this could delay the project. | MM unit has electical equipment difficulty and is unable to finish on deadline. | Video recording equipment would need to be outsourced if the rest of campus cannot assist with video equipment. | MM Unit | low | medium | N/A | Acceptance
|  | Dvp5.3 | 3 | D vid - HR | Delay in completion of videos due to human error and issues | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | First deadline is not met by the MM unit. | Set a second deadline for 3 days and ask for daily progress reports. | MM Unit | low | medium | N/A | Mitigation
|  | Dvp5.4 | 2 | F vid | Failure to complete videos | FF4 | We need the course materials and a meeting with the SME. It is difficult to determine how much time will be needed for course creation outside the estimate given to the committee. | Second deadline is not met by MM unit . | Take video as is and add to the course. Additional video material will be added on the second iteration of the course. | MM Unit | low | high | N/A | Acceptance
| Implementation/Production Close Out | Imp1.1 | 6 | E upload | Early course upload | Tech | Courses can be published to the Canvas system after full team approval. Each team member works separately and has separate schedules. Coordination between the schedules for final approval is sketchy. | All units were able to coordinate and approve the courses before the first deadline. | Fantastic! ID unit assist with Operations Unit in project management of the courses. | ID Unit | medium | low | N/A | Acceptance
|  | Imp1.2 | 3 | D upload | Delay in course upload | Tech | Courses can be published to the Canvas system after full team approval. Each team member works separately and has separate schedules. Coordination between the schedules for final approval is sketchy. | All units were unable to coordinate and approve courses by the first deadline. | Second deadline is created for 1 day so everyone can approve the courses. A meeting will be called where everyone on the project can attend and sign off on the courses. | ID Unit | low | medium | N/A | Mitigation
|  | Imp1.3 | 1 | F upload | Failure to upload course | Tech | Courses can be published to the Canvas system after full team approval. Each team member works separately and has separate schedules. Coordination between the schedules for final approval is sketchy. Unforeseen issues that can pull members from a project permanently, such as hospital stays, hospice care-giver and other such issues are not expected but cannot be controled. | All units were unable to coordinate and approve courses by the second deadline. | Overriding the team member's approval by the project manager. | ID Unit | low | high | N/A | Escalation
|  | Imp2.1 | 5 | E train | Early delivery of training materials to stakeholders | FF4 | Training materials is developed by the entire team. Production of training materials depend on their individual workloads and schedules. | The units were able to coordinate well and produced training material before the deadline. | Job well done, PR unit! | PM Unit | medium | low | N/A | Acceptance
|  | Imp2.2 | 3 | D train | Delay in delivering training materials to stakeholders | FF4 | Training materials is developed by the entire team. Production of training materials depend on their individual workloads and schedules. | The first deadline is missed by the units in producing training material. | A seond deadline is set in 24-hrs. for distribution. | PM Unit | low | medium | N/A | Mitigation
|  | Imp2.3 | 2 | F train | Failure to deliver training materials to stakeholders | FF4 | Training materials is developed by the entire team. Production of training materials depend on their individual workloads and schedules. | The second deadline is missed by the units in producing training material. | Distribution will take place regardless in 24-hrs. after the second deadline is past. | PM Unit | low | medium | N/A | Acceptance
|  | Imp3.1 |  | D prjt mng-tech | Delay in project management due to technical difficulties | Tech | The project is mainly online besides outside manpower. Unforeseen events, such as weather issues and electrical equipment failure can delay production. | Operations unit expereices equipment failure delaying daily operations for 24 hours. | Contact IT for assistance in assessing the equipment and reason for the campus wide delay. Email patrons an update explaining the situation and when the courses will be accessible again. | PM Unit | low | medium | N/A | Acceptance
|  | Imp3.2 |  | D prjt mng - HR | Delay in project management due to human error and issues | FF4 | The project is mainly online but may have issues due to accessibility corrections or files are not being readable from the project site as it is transferred to the working site. | Accessibility and document format issues after the course activation but not publication. | Update the files as needed and test the course again before publishing. | PM Unit | low | low | N/A | Acceptance
|  | Imp3.3 | 2 | F prjt mng - tech | Failure in project management due to technical difficulties | Tech | The project is mainly online besides outside manpower. Unforeseen events, such as weather issues and electrical equipment failure can delay production. Outsourcing a host might be needed. | Operations unit expereices equipment failure delaying daily operations for more than 48 hours. | Contact IT for assistance in assessing the equipment and reason for the campus wide delay. Email patrons an update explaining the situation and when the courses will be accessible again. | PM Unit | low | medium | N/A | Acceptance
|  | Imp3.4 | 2 | F prjt mng - HR | Failure in project management due to human error and issues | FF4 | The project is mainly online but may have issues due to accessibility corrections or files are not being readable from the project site as it is transferred to the working site. Modifications will be needed to avoid long delays. | Accessibility and document format issues after the course activation and publication. | Update the files as needed and test the course again before emailing patrons about the correction and delay. | PM Unit | low | high | N/A | Acceptance
| Evaluation | Eval1.1 | 5 | E eval | Early completion of evaluation and survey performance and format | FF4 | This is contingent on course creation which is determined by several schedulels between the ID and multi-media teammates who have different working schedules. | ID unit and MM unit turn in unti projects ahead of schedule. Eval unit creates evaluation and survey performance format based off of their submissions. | Eval Unit has ID Unit and MM Unit double-check evaluation and survey performace formats. | Eval Unit | high | low | N/A | Acceptance
|  | Eval1.2 | 3 | D eval | Delay in completion of evaluation and survey performance and format | FF4 | This is contingent on course creation which is determined by several schedulels between the ID and multi-media teammates who have different working schedules. | ID unit and MM unit turn in unti projects after first deadline. | Second deadline is set for 1 day and progress reports are requested. | Eval Unit | low | medium | N/A | Mitigation
|  | Eval1.3 | 2 | E eval | Failure of completion of evaluation and survey performance and format | FF4 | This is contingent on course creation which is determined by several schedulels between the ID and multi-media teammates who have different working schedules. | ID unit and MM unit turn in unti projects after second deadline. | Eval Unit creates a generic survey format to be submitted. | Eval Unit | low | medium | N/A | Acceptance
|  | Eval2.1 | 3 | D mid - tech | Delay due to technical difficulties in administering the pilot mid-semester evaluation | Tech | The evaluation is electronic. Unforseen issues with electrical equipment may take place. | Unforseen issues with electrical equipment take place delaying the mid-pilot semester evaluation by 24-hrs. | The evaluation is published and an email sent to patrons describing the delay and its current availlability | Eval Unit | low | medium | N/A | Acceptance
|  | Eval2.2 | 3 | D mid - HR | Delay due to human error and issues in administering the pilot mid-semester evaluation | FF4 | The evaluation after entered needs approval by the project manager. Availablity of the project manager's schedule is to be determined. | The project manager is unable to approve of the mid-semester evaluation by the release date. | The project manager is given 48 hours to sign off on the mid-pilot semester evaluation. | Eval Unit | low | medium | N/A | Mitigation
|  | Eval2.3 | 2 | F mid - tech | Failure due to technical difficulties and issues in administering pilot mid-semester evaluation | Tech | The evaluation is electronic. Unforseen issues with electrical equipment may take place. | Unforseen issues with electrical equipment take place delaying the mid-pilot semester evaluation by 48-hrs. | The evaluation is published and an email sent to patrons describing the delay and its current availlability | Eval Unit | low | medium | N/A | Acceptance
|  | Eval2.4 | 2 | F mid - HR | Failure due to human error and issues in administering pilot mid-semester evaluation | FF4 | The evaluation after entered needs approval by the project manager. Availablity of the project manager's schedule is to be determined. | The project manager is unable to approve of the mid-semester evaluation 48-hrs. after the release date. | The evaluations is published as is with an email to patrons apologizing for the delay and that the evaluation is available. | Eval Unit | low | medium | N/A | Acceptance
|  | Eval3.1 | 3 | D end - tech | Delay due to technical difficulties in administering the pilot end-semester evaluation | Tech | The evaluation is electronic. Unforseen issues with electrical equipment may take place. | Unforseen issues with electrical equipment take place delaying the end-pilot semester evaluation by 24-hrs. | The evaluation is published and an email sent to patrons describing the delay and its current availlability | Eval Unit | low |  | N/A | Acceptance
|  | Eval3.2 | 3 | D end - HR | Delay due to human error and issues in administering the pilot end-semester evaluation | FF4 | The evaluation after entered needs approval by the project manager. Availablity of the project manager's schedule is to be determined. | The project manager is unable to approve of the end-semester evaluation by the release date. | The project manager is given 48 hours to sign off on the end-pilot semester evaluation. | Eval Unit | low |  | N/A | Mitigation
|  | Eval3.3 | 2 | F end - tech | Failure due to technical difficulties in administering the pilot end-semester evaluation | Tech | The evaluation is electronic. Unforseen issues with electrical equipment may take place. | Unforseen issues with electrical equipment take place delaying the end-pilot semester evaluation by 48-hrs. | The evaluation is published and an email sent to patrons describing the delay and its current availlability | Eval Unit | low | medium | N/A | Acceptance
|  | Eval3.4 | 2 | F end - HR | Faliure due to human error and issues in administering pilot end-semester evaluation | FF4 | The evaluation after entered needs approval by the project manager. Availablity of the project manager's schedule is to be determined. | The project manager is unable to approve of the end-semester evaluation 48-hrs. after the release date. | The evaluations is published as is with an email to patrons apologizing for the delay and that the evaluation is available. | Eval Unit | low | medium | N/A | Acceptance
| PR & Marketing | PR1.1 | 3 | I PR | Increase in cost of PR materials | Xmen | Costs estimated in the project charter for PR materials may change after the project charter has been approved. | Cost of PR materials increased. | The program manager needs to find funds or decrease their order size from the PR unit. | PR Unit | low | medium | N/A | Acceptance
|  | PR1.2 | 5 | De PR | Decrease in the cost of PR materials | Xmen | Costs estimated in the project charter for PR materials may change after the project charter has been approved. | Cost of PR materials decreased. | The program manager can increase their order to cover the surplus in funds. | PR Unit | low | low | N/A | Acceptance
|  | PR2.1 | 5 | E PR delivery | Early delivery of PR materials | Xmen | Project content graphic package needs to be complete before PR materials can be created and delivered. | PR unit receives material on-time or early and is able to produce materials before the deadline. | PR has additional time to formulate further distribution possibilities. | PR Unit | medium | low | N/A | Acceptance
|  | PR2.2 | 3 | D PR delivery | Delay in delivery of PR Materials | Xmen | Project content graphic package needs to be complete before PR materials can be created and delivered. | PR unit receives the materials past the deadline by 24-hrs. Materials are created late. | PR has less time to formulate distribution possibilities. | PR Unit | low | medium | N/A | Acceptance
|  | PR2.3 | 2 | F PR delivery | Faliure of PR mateirals to be delivered | Xmen | Project content graphic package needs to be complete before PR materials can be created and delivered. | PR unit receives the materials past the deadline by 48-hrs. Materials are created late. | PR has to use traditional routes of distribution. | PR Unit | low | medium | N/A | Acceptance
|  | PR3.1 | 5 | E PR distribution | Early distribution of PR materials | Xmen | Project content graphic package needs to be complete before PR materials can be created, delivered and distributed. | PR unit creates materials earlier than the deadline. | Additional routes plus the traditional ones can have PR distribution. | PR Unit | medium | low | N/A | Acceptance
|  | PR3.2 | 3 | D PR distribution | Delay in distribution of PR materials | Xmen | Project content graphic package needs to be complete before PR materials can be created, delivered and distributed. | PR unit creates materials 24-hrs. past the deadline. | Only a few new routes plus the traditional ones of the distribution of PR materials. | PR Unit | low | medium | N/A | Acceptance
|  | PR3.3 | 2 | F PR distribution | Failure to distribute PR mateirals | Xmen | Project content graphic package needs to be complete before PR materials can be created, delivered and distributed. | PR unit creates materials 48-hrs. past the deadline. | Only traditional routes of distribution can be used for PR materials. | PR Unit | low | medium | N/A | Acceptance
| Close-out of Project | Clo1.1 | 3 | D final | Delay in final project report creation | FF4 | Evaluation material needs to be completed before the project report can be created. All is contingent on if there no delays in the evaluation data being delivered to the project manager. | There is a 24-hr. delay in distribution evaluation material and delay in sending it to the project managere. | Project manager asks for an update from the Eval unit of when the end-semeter evaluations were distributed and when the data would be ready. | PM Unit | low | low | N/A | Acceptance
|  | Clo1.2 | 2 | F final | Failure in final project report creation | FF4 | Evaluation material needs to be completed before the project report can be created. All is contingent on if there no failures in the evaluation data being compiled and delivered to the project manager. | There is a 48-hr. delay in distribution evaluation material and delay in sending it to the project managere. | Data will be collected and sent to the project manager to compile the final project report. | PM Unit | low | medium | N/A | Acceptance
|  | Clo2.1 | 3 | D lessons | Delay in creating lessons-learned report | FF4 | Lessons-learned is dependant on the project report creation. If there are any delays in its creation it could delay the lessons-learned report creation. | There is a 24-hr. delay in creating the project report. | The project manager is given 48 hours to complete the report. | PM Unit | low | low | N/A | Acceptance
|  | Clo2.2 | 2 | F lessons | Failure to create lessons-learned report | FF4 | Lessons-learned is dependant on the project report creation. If there are any failures in its creation it could stop the lessons-learned report creation. | There is a 48-hr. delay in creating the project report. | The project manager submits the final project report to the committee and asks for a 24-hr. extension on the compiling of the lessons-learned report. | PM Unit | low | medium | N/A | Mitigation
|  |  | Risk Rank |  |  | Risk Abbreviations Key
|  |  | 1 | Disaster |  | D | Delay
|  |  | 2 | Dibacle |  | De | Decrease
|  |  | 3 | Issue |  | E | Early
|  |  | 4 | To be observed |  | F | Failure
|  |  | 5 | Minor success |  | I | Increase
|  |  | 6 | Success
|  |  | 7 | Excelsior! |  | Categories Key
[6 empty] | FF4 | Human Resources Internal
[6 empty] | Xmen | Human Resources External
[6 empty] | Tech | Technology
[6 empty] | T | Time