## Task_Table
ID | Name | Resource_Names | Duration | Start | Finish | Predecessors | Percent_Complete | Outline_Level | Notes | Active | Task_Mode
1 | Project Initiation |  | 8 hrs | 2025-02-06 08:00 | 2025-02-06 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
2 | Define Project Scope and Objectives |  | 4 hrs | 2025-02-07 08:00 | 2025-02-07 12:00 | 1 | 0 | 1 |  | Yes | Auto Scheduled
3 | Identify Project Stakeholders |  | 4 hrs | 2025-02-07 08:00 | 2025-02-07 12:00 | 1 | 0 | 1 |  | Yes | Auto Scheduled
4 | Requirements Gathering Phase |  | 40 hrs | 2025-02-09 08:00 | 2025-02-13 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
5 | Define Data Collection Methodologies |  | 8 hrs | 2025-02-07 13:00 | 2025-02-09 12:00 | 2 | 0 | 1 |  | Yes | Auto Scheduled
6 | Conduct Interviews with Stakeholders |  | 8 hrs | 2025-02-07 08:00 | 2025-02-07 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
7 | Collect Survey Responses |  | 8 hrs | 2025-02-07 08:00 | 2025-02-07 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
8 | Analyze Legal and Compliance Requirements |  | 12 hrs | 2025-02-10 13:00 | 2025-02-11 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
9 | Review Privacy Regulations |  | 6 hrs | 2025-02-10 10:00 | 2025-02-10 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
10 | Review Security Standards |  | 6 hrs | 2025-02-11 10:00 | 2025-02-11 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
11 | Requirements Analysis and Documentation |  | 30 hrs | 2025-02-17 10:00 | 2025-02-20 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
12 | Analyze Stakeholder Input |  | 12 hrs | 2025-02-13 13:00 | 2025-02-14 17:00 | 3 | 0 | 1 |  | Yes | Auto Scheduled
13 | Analyze Interview Data |  | 6 hrs | 2025-02-14 10:00 | 2025-02-14 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
14 | Analyze Survey Data |  | 6 hrs | 2025-02-14 10:00 | 2025-02-14 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
15 | Document Functional Requirements |  | 18 hrs | 2025-02-18 15:00 | 2025-02-20 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
16 | Database Design and Implementation |  | 50 hrs | 2025-02-21 08:00 | 2025-03-03 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
17 | Define Database Schema |  | 20 hrs | 2025-02-21 08:00 | 2025-02-25 12:00 | 4 | 0 | 1 |  | Yes | Auto Scheduled
18 | Define Tables and Relationships |  | 12 hrs | 2025-02-20 13:00 | 2025-02-21 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
19 | Define Data Entry Rules |  | 8 hrs | 2025-02-25 08:00 | 2025-02-25 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
20 | Database Implementation |  | 30 hrs | 2025-02-26 08:00 | 2025-03-03 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
21 | Create Database Tables |  | 16 hrs | 2025-02-26 08:00 | 2025-02-27 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
22 | Implement Data Entry Rules |  | 14 hrs | 2025-03-03 08:00 | 2025-03-04 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
23 | User Interface Design and Development |  | 70 hrs | 2025-03-03 08:00 | 2025-03-13 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
24 | Design User Interface Mockups |  | 30 hrs | 2025-03-03 08:00 | 2025-03-06 15:00 | 5 | 0 | 1 |  | Yes | Auto Scheduled
25 | Create Mockups for Main Pages |  | 18 hrs | 2025-03-03 08:00 | 2025-03-05 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
26 | Gather Feedback on Mockups |  | 12 hrs | 2025-03-10 08:00 | 2025-03-11 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
27 | Develop User Interface |  | 40 hrs | 2025-03-10 08:00 | 2025-03-14 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
28 | Implement Main Page UI |  | 24 hrs | 2025-03-10 08:00 | 2025-03-12 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
29 | Implement Feedback-Driven Revisions |  | 16 hrs | 2025-03-17 08:00 | 2025-03-18 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
30 | Backend Development |  | 90 hrs | 2025-03-17 08:00 | 2025-04-01 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
31 | Develop Core System Logic |  | 40 hrs | 2025-03-17 08:00 | 2025-03-21 17:00 | 6 | 0 | 1 |  | Yes | Auto Scheduled
32 | Implement User Authentication |  | 18 hrs | 2025-03-17 08:00 | 2025-03-19 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
33 | Implement Data Handling Functions |  | 22 hrs | 2025-03-21 08:00 | 2025-03-25 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
34 | Integrate Database Functionality |  | 30 hrs | 2025-03-25 08:00 | 2025-03-28 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
35 | Integrate User Data Handling |  | 16 hrs | 2025-03-25 08:00 | 2025-03-26 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
36 | Integrate Reporting Functionality |  | 14 hrs | 2025-03-31 08:00 | 2025-04-01 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
37 | Implement Security Measures |  | 20 hrs | 2025-04-01 08:00 | 2025-04-03 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
38 | Integration and Testing |  | 50 hrs | 2025-04-04 08:00 | 2025-04-14 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
39 | Integrate UI, Backend, and Database |  | 30 hrs | 2025-04-04 08:00 | 2025-04-09 15:00 | 7 | 0 | 1 |  | Yes | Auto Scheduled
40 | Integrate User Interface and Backend |  | 18 hrs | 2025-04-04 08:00 | 2025-04-08 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
41 | Integrate Database Functionality |  | 12 hrs | 2025-04-08 08:00 | 2025-04-09 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
42 | Conduct System Testing |  | 20 hrs | 2025-04-11 08:00 | 2025-04-15 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
43 | Develop Testing Scenarios |  | 10 hrs | 2025-04-11 08:00 | 2025-04-14 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
44 | Perform System Testing |  | 10 hrs | 2025-04-14 08:00 | 2025-04-15 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
45 | Bug Fixing and Final Testing |  | 10 hrs | 2025-04-16 08:00 | 2025-04-17 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
46 | Security and Compliance Implementation |  | 30 hrs | 2025-04-17 08:00 | 2025-04-22 15:00 |  | 0 | 1 |  | Yes | Auto Scheduled
47 | Data Encryption and Security Measures |  | 20 hrs | 2025-04-17 08:00 | 2025-04-21 12:00 | 8 | 0 | 1 |  | Yes | Auto Scheduled
48 | Compliance with Privacy Regulations |  | 10 hrs | 2025-04-21 08:00 | 2025-04-22 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
49 | Training Material Development |  | 20 hrs | 2025-04-22 08:00 | 2025-04-24 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
50 | Create Training Modules |  | 10 hrs | 2025-04-22 08:00 | 2025-04-23 10:00 | 9 | 0 | 1 |  | Yes | Auto Scheduled
51 | Develop User Guides |  | 10 hrs | 2025-04-25 08:00 | 2025-04-28 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
52 | User Training |  | 40 hrs | 2025-04-28 08:00 | 2025-05-02 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
53 | Develop Training Schedule |  | 15 hrs | 2025-04-28 08:00 | 2025-04-29 16:00 | 10 | 0 | 1 |  | Yes | Auto Scheduled
54 | Conduct Training Sessions |  | 25 hrs | 2025-04-30 08:00 | 2025-05-05 09:00 |  | 0 | 1 |  | Yes | Auto Scheduled
55 | System Rollout |  | 20 hrs | 2025-05-05 08:00 | 2025-05-07 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
56 | Pre-Rollout Checklist |  | 10 hrs | 2025-05-05 08:00 | 2025-05-06 10:00 | 11 | 0 | 1 |  | Yes | Auto Scheduled
57 | Launch System to Users |  | 10 hrs | 2025-05-08 08:00 | 2025-05-09 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled
58 | Project Closure and Evaluation |  | 16 hrs | 2025-05-09 08:00 | 2025-05-12 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
59 | Evaluate Project Success |  | 8 hrs | 2025-05-09 08:00 | 2025-05-09 17:00 | 12 | 0 | 1 |  | Yes | Auto Scheduled
60 | Document Lessons Learned |  | 8 hrs | 2025-05-12 08:00 | 2025-05-12 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
61 | Documentation and Knowledge Transfer |  | 36 hrs | 2025-05-13 08:00 | 2025-05-19 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
62 | Create User Manuals |  | 32 hrs | 2025-05-13 08:00 | 2025-05-16 17:00 | 13 | 0 | 1 |  | Yes | Auto Scheduled
63 | Develop Technical Documentation |  | 20 hrs | 2025-05-16 08:00 | 2025-05-20 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
64 | Post-Implementation Review |  | 24 hrs | 2025-05-19 08:00 | 2025-05-21 17:00 |  | 0 | 1 |  | Yes | Auto Scheduled
65 | Gather User Feedback |  | 12 hrs | 2025-05-19 08:00 | 2025-05-20 12:00 | 14 | 0 | 1 |  | Yes | Auto Scheduled
66 | Evaluate System Performance |  | 12 hrs | 2025-05-20 08:00 | 2025-05-21 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
67 | Project Closure and Reporting |  | 20 hrs | 2025-05-22 08:00 | 2025-05-26 12:00 |  | 0 | 1 |  | Yes | Auto Scheduled
68 | Finalize Project Documentation |  | 10 hrs | 2025-05-22 08:00 | 2025-05-23 10:00 | 15 | 0 | 1 |  | Yes | Auto Scheduled
69 | Generate Project Report |  | 10 hrs | 2025-05-26 08:00 | 2025-05-27 10:00 |  | 0 | 1 |  | Yes | Auto Scheduled

## Resource_Table
ID | Name | Email_Address | Type | Material_Label | Initials | Group | Max_Units | Standard_Rate | Cost_Per_Use | Notes

## Assignment_Table
Task_Name | Resource_Name | Percent_Work_Complete | Work | Assignment_Units